# Synthesis of Findings

ETHEREUM × UN IMPACT FRAMEWORK

DESIGN & IMPLEMENTATION TOOLKIT

Authors: Selin Arpaci & Teodor Petricevic

Contributing editor: Razali Samsudin

# Synthesis of Findings

This synthesis explains how the framework was developed and how UN agencies and Ethereum developers can utilize it to design, evaluate, and replicate impact projects.

1. THEORY OF CHANGE	3

PROBLEM STATEMENT	3

KEY ASSUMPTIONS TO TEST	4

INTENDED OUTCOMES	4

2. ACTIVITIES AND EVIDENCE BUILDING MILESTONES	5

MILESTONE 1: MAPPING THE ECOSYSTEM	5

MILESTONE 2: ASSESSMENT & SELECTION	5

MILESTONE 3: FRAMEWORK CO-DESIGN	6

MILESTONE 4: FINAL SYNTHESIS & DELIVERY	6

2. FROM THEORY TO PRACTICE: HOW TO UTILIZE OUR WORK?	7

3. STEP BY STEP BASELINE PROJECT DESIGN AND IMPLEMENTATION GUIDELINE	8

STAGE 0: FAMILIARIZE (Entry + workflow orientation)	9

STAGE 1: IDENTIFY (Inspire + Discover)	9

1.1, Inspire: Impact Stories as Proof of Feasibility	9

1.2. Discover: identify problem spaces where these patterns can transfer	10

STAGE 2: UNDERSTAND (Review + Map)	11

2.1. Review: what “good” looks like (standards + evaluation logic)	11

2.2.  Map: understand the current user/service journey (“as-is”)	11

STAGE 3: IMAGINE (Alternate realities + ideation)	12

STAGE 4: SITUATE (ToC + operating model)	12

STAGE 5: DESIGN (Ops + M&E + Governance + Tech)	13

STAGE 6: VALIDATE (Readiness checks + conditions)	14

STAGE 7: DELIVER (Deploy + Assess + Iterate)	15

7.1. Develop & deploy + assess + ecosystem pulse	15

7.2. Adapt + scale and institutionalize	15

4. FURTHER TOOLS IN THE TOOLBOX	16

STAGE 1: IDENTIFY (Inspire + Discover)	16

Tool 1: Pattern Card	16

Tool 2: Problem Statements [Candidate use cases]	17

Tool 3: Fit-for-Blockchain Decision Gate	18

STAGE 2: UNDERSTAND (Review + Map)	18

Tool 4: As-Is Journey + Constraints Map	19

Tool 4: Minimum Evidence Set Extractor (UN + Web3 Standards)	19

A. UN-aligned evidence checklist (minimum)	19

B. Web3-native evidence checklist (minimum)	20

C. Triple-Proof Mapping Sheet	20

STAGE 3: IMAGINE (Alternate realities + ideation)	21

Tool 5: 3-option concept + tradeoff log (incl. non-blockchain alternative)	21

STAGE 4 — SITUATE (ToC + operating model)	22

Tool 6: Mini-ToC builder (IF→THEN with assumptions/tests/gates)	22

STAGE 5 — DESIGN (Ops + M&E + Governance + Tech)	24

Tool 7: Operational Workflow Template	24

Tool 8: Governance workflow/committee charter template	24

Tool 9: Technical architecture + data-flow split (on-chain vs off-chain) template	25

Tool 10: Modelling, measurement & assessment mechanisms	25

STAGE 6 — VALIDATE (Readiness checks + adversarial tests)	26

Tool 11: Readiness checklist (tech + safeguards + evaluation + capacity + procurement)	26

Tool 12: Consent audit + bias review	26

STAGE 7 — DELIVER (Deploy + assess + ecosystem pulse)	27

Tool 13: Data Flows + tracking (transactions/audits/narratives/convergence)	27

Tool 14: Committee meeting agenda (decision + documentation)	27

Tool 15: Privacy checklist	28

Tool 16: Ethics inbox (safe reporting channel)	28

Tool 17: Registry submission pack + reflections	28

Additional helpful templates	29

Motivations	29

Project purpose statement	29

ESEG DOMAIN PRIORITIZATION	30

METRIC PICKING MATRIX	30

Participatory Metric Refinement	31

3-PAGE IMPACT REPORT	32

5. Delivery Deck– inspired by WFP Building Blocks	32

0. Cover Page (BB)	33

1. Executive Summary (BB)	33

1.1 Problem	33

1.2 Solution	33

1.3 Why blockchain / Ethereum	33

1.4 What changed (outcomes)	33

1.5 How we know (Triple-Proof)	34

1.6 Key safeguards	34

2. Pattern Card (BB)	34

3. Fit-for-Blockchain Decision Gate (BB)	35

3.1 Candidate problem statements	35

3.2 Problems identified for the use case (5 Why framework results)	35

3.3. Why blockchain adds value (BB framing):	35

3.4. Minit ToC	35

4. Minimum Evidence Set (BB)	35

4.1 UN-aligned minimum checklist (BB)	35

4.2 Web3-native minimum checklist (BB)	36

4.3 Triple-Proof mapping (BB sample indicators)	36

5. Design Blueprint	36

5.1. Governance	36

5.2. Technical Architecture + data flows	37

5.3. Operational workflows	37

5.4. Measurement and Assessment	37

5.5. Data Reporting Plan	37

Data Tracking Dashboard	38

COMMITTEE MEETING AGENDA (Monthly, 90 Min) - Example	38

PRIVACY CHECKLIST (Weekly)	38

6. Validate (BB)	38

7. Reporting	39

Lifecycle Reporting (used as an example, not verified)	40

5. ACKNOWLEDGEMENTS	41

# 1. THEORY OF CHANGE

The Ethereum x UN Impact Framework is built on the premise that credible, comparable, and verifiable impact measurement in blockchain-enabled initiatives requires combining institutional rigor with Web3-native innovation.

## PROBLEM STATEMENT

Over the past decade, blockchain has quietly moved from whitepapers and pilots into the core workflows of humanitarian and development institutions. UN agencies now use distributed ledgers to trace food aid, manage digital identities, issue climate credits, and prototype new forms of public finance. Yet this activity remains fragmented, unevenly documented, and weakly understood. We lack a clear answer to a simple question: when does blockchain use in development reliably create public value – and when is it just infrastructure in search of a problem?

Today, most blockchain-enabled impact faces systemic blind spots:

- Impact claims are often local, siloed, or anecdotal. There is no shared understanding of where, how, and why blockchain is being deployed across the UN system and adjacent ecosystems.

- Impact is challenging to evaluate because it is defined and perceived differently across various stakeholders, including agencies, builders, beneficiaries, and donors.

- Evidence is fragmented due to a lack of common understanding and limited comparability and standardization across on-chain signals, off-chain reports, and narratives.

- Successful pilots are difficult to replicate without shared templates, pathways, and verification practices.

## KEY ASSUMPTIONS TO TEST

To test this assumption and achieve these goals, we assemble a multi-layered evidence base that informs a coherent pathway from exploration to long-term impact. Multiple data and expertise-rich inputs/ components.

- Ecosystem mapping and verification of Ethereum–UN initiatives

- Empirical evidence from authorized impact stories

- UN evaluation and measurement practices (standards, norms, results frameworks)

- Web3-native evaluation approaches (on-chain signals, governance diagnostics, incentive models)

- Expert feedback from UN agencies, Ethereum ecosystem contributors, and impact organizations

## INTENDED OUTCOMES

Short-term:

- Shared vocabulary for “impact” across agencies and builders

- Higher visibility of blockchain-enabled impact initiatives

- Better understanding of the potentials and challenges of blockchain-enabled impact

Mid-term:

- More comparable reporting across pilots

- Higher-quality project design (clear ToC, safeguards, verification plan)

- Increased trust and collaboration readiness between UN agencies and Web3 teams

Long-term:

- Replicable, verifiable, and scalable blockchain-enabled initiatives that deliver measurable progress on SDG-aligned outcomes, while meeting UN-grade standards for accountability and safeguards.

# 2. ACTIVITIES AND EVIDENCE BUILDING MILESTONES

This section outlines the evidence-based methodology used to develop the Ethereum x UN Impact Framework, filtering mapped potential use cases down to a validated, operational toolkit.

## MILESTONE 1: MAPPING THE ECOSYSTEM

*Establishing the baseline of Ethereum-UN collaboration.

/ Identification: Scanned the landscape to identify 82 potential Ethereum x UN use cases

/ Verification: Filtered for technical reality, confirming 51 verified projects actively built on Ethereum

/ Output: Produced a “Mapping Exercise Report” synthesizing early IMM (Impact Measurement & Management) lessons learned from these pilots

## MILESTONE 2: ASSESSMENT & SELECTION

*Filtering for high-value, replicable models.

/ Shortlisting: Selected 11 use cases as the most illustrative examples of successful Ethereum x UN collaboration

/ Deep Dives: Prioritized 5 standout use cases for in-depth analysis

/ Output: Authored 5 authorized Impact Stories, detailing the problem, solution, and verifiable outcomes/impacts for each.

## MILESTONE 3: FRAMEWORK CO-DESIGN

*Synthesizing best practices into a unified standard.

/ Triple research: Developed three foundational reports:

*UN IMM Practices Report: Auditing existing UN standards (RBM, SDGs, etc.)

*Web3 IMM Practices Report: Analyzing Web3 IMM methodologies

*Ethereum IMM use cases - Impact stories

/ The Bridge: Developed the Ethereum x UN Impact Framework, merging institutional rigor with on-chain transparency

/ Operationalization: Created the Project Design & Implementation Toolkit, a practical guide based directly on the framework.

## MILESTONE 4: FINAL SYNTHESIS & DELIVERY

*Ensuring usability and adoption.*

/ Consolidation: Developed final guidelines as a navigable synthesis.

- We triangulated insights from empirical case studies, theoretical approaches, and applied frameworks.

- Synthesizing cross-system learnings into a taxonomy of blockchain impact pathways

- Identifying convergences between SDG frameworks and Web3-native evaluation models

- Developing hybrid impact metrics linking on-chain signals with human-centered outcomes

- Designing templates, guidelines, and decision trees for UN agencies and implementers

- Developing recommendations with experts from UN agencies, the Ethereum ecosystem, and impact organizations

/ Integration: Linked all research outputs (Mapping, Framework Analysis, Impact Stories) into a cohesive, easy-to-use package for UN agencies and Ethereum builders.

- ETH x UN Impact Framework

# 2. FROM THEORY TO PRACTICE: HOW TO UTILIZE OUR WORK?

This work is designed to be used as a workflow, not as a one-time report. It supports both UN teams and Ethereum builders in transitioning from evidence and examples to a measurable, verifiable, and implementable project—and in continuously improving it through iteration.

Identify (Inspire & Discover) → Understand (Review & Map)→ Imagine→ Situate→ Design → Validate→ Deliver (Develop, assess, iterate)

The table below summarizes the key stages and phases, which are intentionally cyclical and iterative. The first-time (Baseline) flow describes the steps to be followed as a baseline, which are detailed in the next section.

| Phases | META MAPPING OF STAGES |  |  |
| --- | --- | --- | --- |
|  | Stage | First Time (Baseline) | Later Development Cycles |
| Identify | Inspire | Review impact stories → extract patterns | Add new stories + lessons learned from your own pilots (what actually worked/failed) |
|  | Discover | Shortlist candidate problem space(s) + “why blockchain may add value” | Re-scan opportunities using new constraints, feedback, and ecosystem shifts |
| Understand | Review new information | Review framework + UN/Web3 evaluation logic (what “good” looks like) | Review assessment results, audit findings, user feedback, monitoring data |
|  | Map current workflows | Map current user/service journey, constraints, risks, stakeholders | Update journey and constraints with field learnings + participatory insights |
| Imagine | Ideate (Alternate Realities & Ideation) | Generate 2–3 plausible solution concepts (incl. non-blockchain options) that respond to constraints. | Co-create improvements with stakeholders; test alternative designs as conditions change. |
| Situate | Ground (Operational Reality) | Adapt chosen concept to context: ToC, intended impact, stakeholders needed, what changes and how. | Re-ground ToC after pilot evidence; participatory validation of “what matters.” |
| Design | Operational Workflow | Specify operational workflows, stakeholder roles, etc. | Improve usability, reduce burden, strengthen governance, interoperability, privacy/security; update evaluation mechanisms. |
|  | Measurement & Assessment | Build ToC + select indicators + define Triple-Proof plan |  |
|  | Governance Workflow | Design governance mechanisms, desired behaviors, and incentives consider unintended potential outcomes. |  |
|  | Technical Architecture & Data flows | Design technical architecture and data flow in line with the workflows, measurement plan, governance, and design conditions. |  |
| Validate | Readiness Checks | Run readiness checks: technical feasibility, partner capacity, safeguards, evaluation readiness, cost/time realism. | Re-validate after changes, scaling, or new environments |
|  | Check design conditions | Validate if design conditions are met, and if monitoring is embedded in design (e.g. Scalability, replicability, monitoring by design). |  |
| Deliver | Develop, Deploy | Build MVP, onboard stakeholders | Iterate releases; run A/B or phased rollouts |
|  | Assess, Measure | Set up evaluation mechanisms, run pilot; do baseline measurement. | Continuous monitoring + periodic evaluation + participatory sensemaking |
|  | Ecosystem Pulse | Continuously identify changes in the system | Record and assess impact of changes. |
|  | Adapt, Scale & Institutionalize | Use pilot learning to adapt (scope, workflows, metrics, governance). | Scale only when conditions hold; institutionalize templates, procurement docs, training, registry updates. |

# 3. STEP BY STEP BASELINE PROJECT DESIGN AND IMPLEMENTATION GUIDELINE

The tools and decision gates are inspired by the previous

## STAGE 0: FAMILIARIZE (Entry + workflow orientation)

The workflow is cyclical: Test results feed back into Translate/Design, and new insights update Inspire/Discover over time. Users can enter at different points (e.g., agencies reviewing an existing pilot, builders designing a new one).

Familiarize yourself with the workflow:

- Review the workflow stages and gates.

- Choose your entry point.

Entry Points:

- UN agency evaluating a proposal or plot: Use standards to assess credibility, require minimum evidence, validate safeguards, then refine.

  - Understand → design → validate → deliver

- Builder designing a new project: Start from proven patterns, identify a fit-for-purpose problem space, then build evidence-by-design.

  - Identify (Inspire & Discover) → Understand (Review & Map)→ Imagine→ Situate→ Design → validate

- Technical crypto-builders: Translate existing concepts into evaluation-ready designs and proofs.

  - Design → validate → deliver

- Joint UN–builder pilot team: Align on what counts as value and proof, then co-design implementation and verification.

Output: selected entry pathway + named owner(s) for evidence, safeguards, governance, and technical implementation.

## STAGE 1: IDENTIFY (Inspire + Discover)

### 1.1, Inspire: Impact Stories as Proof of Feasibility

Inspiration is grounded in what has already worked. Use:

- UN initiated and Web3-native impact stories to see concrete examples of:

  - Problems addressed and the target group

  - Solutions proposed & workflows (who does what, how, when)

  - Blockchain-enabled mechanisms (how blockchain contributes)

  - Measurable outputs/outcomes

As a result, you can see what successful UN x Ethereum projects achieved. The selected examples can help you identify a library of patterns (“this type of mechanism works in this context”) and evidence examples you can reuse.

Output: a short list of reusable “patterns” (mechanism + workflow + evidence) relevant to your context.

### 1.2. Discover: identify problem spaces where these patterns can transfer

Discovery translates learning into opportunity scanning. Use discovery questions and decision gates to identify and filter out cases where blockchain adds complexity without value.

- Discovery questions to identify high-fit contexts:

  - Where do we see fragmented trust, disputed records, or weak auditability?

  - Where do we see multi-actor coordination problems (many implementers, donors, vendors, agencies)?

  - Where would programmable rules reduce leakage, delays, or disputes?

  - Where would shared infrastructure reduce duplication across agencies?

Output: Draft 2–3 candidate problem statements and answer: why blockchain may add value. Select the one you think has the greatest potential and proceed to the decision gate.

Decision Gate 1 — Fit-for-blockchain

- Sections “When is the Blockchain the right technology? Pre-adoption Value Assessment” and “Environmental readiness, design, and technical performance as preconditions for impact” provide ex-ante criteria to rule out cases where other digital systems would be more appropriate.

- Additionally, check and proceed if there are no red flags:

  - blockchain is mainly added for “transparency optics”

  - governance responsibility is unclear or unacceptable

  - data/privacy risks cannot be mitigated

  - the problem can be solved more effectively with simpler digital systems

- If Gate 1 fails:

  - Stop blockchain pathway OR

  - Check other ideas OR

  - return to Discover (reframe problem) OR

  - return to Inspire (find a better-fit pattern).

As a result, you can have a short list of candidate use cases/problem statements that pass the “blockchain adds value” test.

## STAGE 2: UNDERSTAND (Review + Map)

### 2.1. Review: what “good” looks like (standards + evaluation logic)

Review establishes a shared baseline for credibility and comparability. Use:

- UN-aligned common impact evaluation approaches and frameworks to understand what UN agencies recognize as valid evidence (results chains, SDG alignment, safeguards, evaluation quality, methodological rigour).

- Tech-Agnostic or Web3-native Impact Frameworks & Guidelines to understand how blockchain communities generate and interpret evidence leveraging innovative approaches, on-chain and off-chain signals (on-chain traces, governance signals, incentive alignment, public-goods funding logics).

- Narratives to Lessons synthesizes common themes and recommendations emerged from Web3 Use Cases to design an impact project or framework in Web3.

- A set of recommendations are included within each of these reports for crypto project developers and impact evaluators, helping you in identifying which real-world coordination or accountability problems might benefit from blockchain-enabled mechanisms and/or offchain strategies.

As a result, you will have an understanding of UN and Web3 measurement standards, best practices, recommendations, and key evaluation approaches. You will discover Ethereum-native impact measurement in action.

Output: Derive a Minimum Evidence Set: what must be measured, what must be verified, what safeguards must be met.

### 2.2.  Map: understand the current user/service journey (“as-is”)

Mapping grounds the work in operational reality.

- Map current workflow: actors, decision points, money/data flows, failure points.

- Document constraints: connectivity, identity/access, literacy, local partner capacity, procurement realities.

- Identify risks and stakeholders (including data responsibility/accountability).

Decision Gate 2 — Context clarity

Proceed only if you can clearly define:

- who the users/beneficiaries are and their constraints,

- who controls decisions, data, and resources,

- what the current bottleneck is (trust, time, leakage, disputes, exclusion, etc.)

If Gate 2 fails: Return to Map (collect missing info) OR return to Identify (wrong problem choice).

Output: current-state journey map + stakeholder map + constraints & risks list.

## STAGE 3: IMAGINE (Alternate realities + ideation)

Imagine generates viable solution options before committing to one design.

- Generate 2–3 solution options, including at least one non-blockchain alternative.

- Compare options in terms of feasibility, safeguards, evidence generation, and partner capacity.

- Select the most promising option and record tradeoffs.

Decision Gate 3 — Option viability

Proceed only if the selected option:

- can plausibly operate under real constraints,

- can generate the Minimum Evidence Set,

- has a credible safeguarding approach

- has a realistic stakeholder/governance model

If Gate 3 fails: Return to Imagine (new option set) OR to Understand/Map (constraints misunderstood).

Output: chosen option + tradeoff log + selection rationale.

## STAGE 4: SITUATE (ToC + operating model)

Translating turns the idea into an evaluation-ready causal model. Use:

- The ETHxUN Impact Framework

- Narratives to Lessons synthesizes common themes and recommendations that emerged from Web3 Use Cases to design an impact project or framework in Web3.

Situate turns the chosen concept into an evaluation-ready and context-grounded operating model.

- Build a Theory of Change (activities → outputs → outcomes → impact)

- Align with SDG/RBM where relevant

- Select relevant ESEG domains

- Define key assumptions, risks, and safeguard requirements

- Define “minimum viable measurement plan” (what must be tracked from day one)

- Define operating model: stakeholders needed, roles, responsibilities, accountability.

Decision Gate 4 — Measurement & ethics feasibility

Proceed only if:

- outcomes can be measured ethically and feasibly within time/budget/access constraints

- data collection does not create unacceptable privacy/exclusion harms

- Triple-Proof evidence is feasible (on-chain/off-chain/human outcome proof)

If Gate 4 fails: Return to Situate (revise ToC/indicators) OR return to Imagine (choose different option).

Output: measurement-ready ToC + indicator shortlist linked to outcomes (not only outputs). + Triple-Proof plan + operating model.

## STAGE 5: DESIGN (Ops + M&E + Governance + Tech)

Design ensures that the implementation can generate credible proof—not as an afterthought.

- Operational workflow: specify the new “to-be” workflow, including who does what, when, and how.

- Governance workflow: define decision-making, incentives, accountability, dispute resolution, stakeholder relationships.

- Technical architecture: define what is logged on-chain vs off-chain, access control, auditability, privacy/security, integration points.

- Modelling, measurement & assessment mechanisms: implement the measurement plan (data sources, cadence, dashboards, evaluation moments).

Use the Toolkit templates to specify:

- the blockchain mechanism and user journey (who does what, when, with what data)

- governance/accountability roles (UN, implementer, auditors, community, tech team)

- data collection plan (what is logged, where, and why)

- safeguards and inclusion requirements

Decision Gate 5— Design completeness

Proceed only if:

- Roles and responsibilities are unambiguous (governance-ready)

- Data flows support the Triple-Proof plan (evidence ready)

- Safeguards are implementable (safety ready)

- The operational workflow is realistic for partners (capacity ready)

- Evidence is produced by default/ embedded in-design

If Gate 5 fails:

- governance unclear → return to Governance workflow

- proof not feasible → return to M&E or Tech

- safeguards fail → return to Situate (revise risks/assumptions) and Design

- workflow unrealistic → return to Map and redesign

Output: full project blueprint (ops + M&E + governance + tech) + pilot protocol draft.

## STAGE 6: VALIDATE (Readiness checks + conditions)

Validate feasibility, safety, and evidence quality early Testing makes the framework practical and adoption-ready. Test includes:

- technical feasibility (does the mechanism work at realistic scale?)

- evaluation feasibility (can we actually measure the intended outcomes?)

- safeguard feasibility (privacy, security, inclusion, harm prevention)

- verification feasibility (can we produce Triple-Proof evidence reliably?)

- partner capacity and resourcing (time, skills, budget)

- compliance/procurement conditions (where applicable)

As a result, you will have a pilot learning report + adjustments to design and metrics.

Decision Gate 6 — Go / No-Go

- Go: pilot can proceed with clear mitigations and monitoring triggers

- Conditional Go: proceed only after specified fixes (return to Design/Situate)

- No-Go: stop or re-scope; return to Identify/Understand

Output: Go/No-Go decision + mitigation plan + updated pilot protocol.

## STAGE 7: DELIVER (Deploy + Assess + Iterate)

### 7.1. Develop & deploy + assess + ecosystem pulse

Deliver executes the pilot and produces baseline evidence. Continuously Assess & Iterate: learn, refine, and standardize for replication

- develop MVP and deploy pilot (phased rollout)

- onboard relevant stakeholders (implementers, evaluators, auditors, community)

- set up evaluation mechanisms and dashboards

- run baseline measurement and monitoring

- take an “ecosystem pulse” (policy shifts, partner landscape, technical shifts) and log changes to assumptions

Decision Gate 7 — Harm / Evidence trigger

- If evidence is weak/inconclusive → return to Situate (revise ToC/indicators) and Design (instrumentation)

- If harm/exclusion occurs → pause and return to Situate + Design (safeguards redesign)

- If adoption fails due to workflow burden → return to Design (simplify workflow)

Output: pilot results + baseline evaluation memo + change log + revised risk register.

### 7.2. Adapt + scale and institutionalize

Iteration converts the pilot into a replicable and scalable model.

- adapt ToC, indicators, workflows, governance, and tech based on pilot learning

- standardize templates and documentation

- prepare procurement-ready materials (where relevant)

- update registry entry and replication notes

- run training/workshops for adoption

Decision Gate 8 — Scale readiness

Scale only if:

- safeguards hold under expansion

- governance and accountability scale with additional actors

- measurement remains feasible without disproportionate burden

- funding/operations sustainability is credible

If Gate 8 fails: remain in Deliver/Iterate cycles until prerequisites hold.

Output: replication-ready package + scale plan + institutionalization assets.

# 5. ACKNOWLEDGEMENTS

This project was funded through the Next Billion (NxB) Fellowship. The work was led primarily by Teodor Petricevic (project owner) and Selin Arpaci, who together steered the end-to-end development of the research outputs and final deliverables.

Teodor Petricevic provided overall project ownership, strategic alignment across all milestones, and communicated expectations from both the UN and Ethereum communities. He played a key role in ensuring quality across all milestones.

Selin Arpaci played a central role in achieving milestones, with primary responsibility for establishing the evidence base and synthesis. This included conducting comprehensive research on impact measurement and evaluation frameworks; gathering, analyzing, and synthesizing qualitative and quantitative inputs; conducting and coordinating expert interviews; leading open feedback cycles with stakeholders across the UN and Ethereum ecosystems; iterating on earlier milestones; and producing the final integrated outputs, including the framework and implementation toolkit.

Contributions to Milestones 1 and 2—ecosystem mapping and case study development—were also supported by Simon Testot and Asem Al-Hammadi who contributed to mapping the UN landscape and assisted with interviews and data collection for the UN-led initiatives relevant to blockchain.

We also thank Razali Samsudin, who contributed substantive editorial and conceptual input, including governance design, ethical safeguards, and narrative-based validation logic, with direct textual contributions across the framework and implementation toolkit.

Finally, we are grateful to all survey respondents and expert interview participants from UN agencies, Ethereum ecosystem organizations, and impact initiatives who shared insights, practical constraints, and feedback throughout the process. Where individuals have not explicitly consented to being named, we acknowledge them collectively by organization or project to respect confidentiality and participation norms.

When is the Blockchain the right technology? Pre-adoption Value Assessment